{"text_format":"1","workbook":"xlsx","n_sheets":26,"sheets":["Rev.Arena","Rev.POP","Menu","Proj.beställning","Rev.historik","Lärdomar","Intressenter","Funk.str","Lev.str","Arb.str","Produktbacklog","Visualisering","Organisation","Resursplan","Kom.plan","Gantt&MS","Risker","Risk Åtg.","Möjligheter","Möjl.Åtg","Budget","Status","Beslutslogg","Ändringslogg","DA","Admin"],"not_rendered":{"charts":0,"images":12,"macros":1,"external_links":0,"defined_names":234,"comments":11,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Rev.Arena","index":0,"n_rows":9,"n_cols":7,"rows_kept":9,"cut":false,"hidden":true,"merged":[[8,4,8,8],[3,6,3,8],[4,6,4,8],[5,6,5,8],[3,3,3,4],[4,3,4,4],[5,3,5,4],[1,1,1,2],[2,1,2,2],[3,1,3,2],[4,1,4,2],[5,1,5,2],[9,4,9,8],[42,4,42,8],[43,4,43,8],[44,4,44,8],[45,4,45,8],[10,4,10,8],[11,4,11,8],[12,4,12,8],[13,4,13,8],[14,4,14,8],[15,4,15,8],[16,4,16,8],[17,4,17,8],[18,4,18,8],[19,4,19,8],[22,4,22,8],[46,4,46,8],[47,4,47,8],[48,4,48,8],[49,4,49,8],[20,4,20,8],[21,4,21,8],[37,4,37,8],[38,4,38,8],[39,4,39,8],[40,4,40,8],[41,4,41,8],[24,4,24,8],[25,4,25,8],[26,4,26,8],[27,4,27,8],[28,4,28,8],[23,4,23,8],[34,4,34,8],[35,4,35,8],[36,4,36,8],[29,4,29,8],[30,4,30,8],[31,4,31,8],[32,4,32,8],[33,4,33,8]]}
[]
[null,null,null,"Revisionshistorik - Projektets Arena."]
[]
[null,"Projektnummer:",null,{"$f":"Projektnummer","v":" "},null,"Projektnamn:",{"$f":"Projektnamn","v":"Projektnamn"}]
[null,"Projektets Sponsor:",null,{"$f":"Sponsor","v":" "},null,"Projektledare:",{"$f":"Projektledare","v":" "}]
[null,"Site/Plats:",null,{"$f":"Site","v":" "},null,"Affärsenhet:",{"$f":"Affärsenhet","v":" "}]
[]
[]
[null,"Nr","Datum","Uppdaterad av:","Kommentar"]

{"sheet":"Rev.POP","index":1,"n_rows":9,"n_cols":7,"rows_kept":9,"cut":false,"hidden":true,"merged":[[4,1,4,2],[4,3,4,4],[4,6,4,8],[1,1,1,2],[2,1,2,2],[3,1,3,2],[3,3,3,4],[3,6,3,8],[16,4,16,8],[5,1,5,2],[5,3,5,4],[5,6,5,8],[8,4,8,8],[9,4,9,8],[10,4,10,8],[11,4,11,8],[12,4,12,8],[13,4,13,8],[14,4,14,8],[15,4,15,8],[28,4,28,8],[17,4,17,8],[18,4,18,8],[19,4,19,8],[20,4,20,8],[21,4,21,8],[22,4,22,8],[23,4,23,8],[24,4,24,8],[25,4,25,8],[26,4,26,8],[27,4,27,8],[40,4,40,8],[29,4,29,8],[30,4,30,8],[31,4,31,8],[32,4,32,8],[33,4,33,8],[34,4,34,8],[35,4,35,8],[36,4,36,8],[37,4,37,8],[38,4,38,8],[39,4,39,8],[47,4,47,8],[48,4,48,8],[49,4,49,8],[41,4,41,8],[42,4,42,8],[43,4,43,8],[44,4,44,8],[45,4,45,8],[46,4,46,8]]}
[]
[null,null,null,"Revisionshistorik - Projektets Operativa Plan."]
[]
[null,"Projektnummer:",null,{"$f":"Projektnummer","v":" "},null,"Projektnamn:",{"$f":"Projektnamn","v":"Projektnamn"}]
[null,"Projektets Sponsor:",null,{"$f":"Sponsor","v":" "},null,"Projektledare:",{"$f":"Projektledare","v":" "}]
[null,"Site/Plats:",null,{"$f":"Site","v":" "},null,"Affärsenhet:",{"$f":"Affärsenhet","v":" "}]
[]
[]
[null,"Nr","Datum","Uppdaterad av:","Kommentar"]

{"sheet":"Menu","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[]}

{"sheet":"Proj.beställning","index":3,"n_rows":46,"n_cols":7,"rows_kept":46,"cut":false,"hidden":false,"merged":[[28,1,28,2],[29,1,29,2],[30,1,30,2],[31,1,31,2],[32,1,32,2],[23,1,23,2],[24,1,24,2],[25,1,25,2],[26,1,26,2],[27,1,27,2],[31,4,31,5],[32,4,32,5],[1,2,1,6],[3,1,3,2],[4,1,4,2],[5,1,5,2],[6,1,6,2],[3,5,3,6],[4,5,4,6],[5,5,5,6],[6,5,6,6],[9,1,9,2],[19,1,19,2],[20,1,20,2],[21,1,21,2],[22,1,22,2],[26,4,26,5],[27,4,27,5],[28,4,28,5],[29,4,29,5],[30,4,30,5],[12,4,12,5],[9,3,9,6],[23,4,23,5],[24,4,24,5],[25,4,25,5],[13,4,13,5],[14,4,14,5],[15,4,15,5],[16,4,16,5],[17,4,17,5],[18,4,18,5],[19,4,19,5],[20,4,20,5],[21,4,21,5],[22,4,22,5],[45,1,45,2],[33,4,33,5],[34,4,34,5],[37,5,37,6],[38,5,38,6],[34,1,34,2],[39,1,39,2],[38,1,38,2],[41,1,42,3],[43,1,43,2],[44,1,44,2],[33,1,33,2],[37,1,37,2],[13,1,13,2],[12,1,12,2],[11,1,11,2],[18,1,18,2],[17,1,17,2],[16,1,16,2],[15,1,15,2],[14,1,14,2]]}
[]
[]
[null,null,"Datum då filen senast sparades:",{"$f":"TODAY()","v":"2024-01-11"}]
[null,"Projektnamn:",null,"Projektnamn","Projektnummer:"," "]
[null,"Projektledare:",null," ","Projektbeställare:"," "]
[null,"Plats:",null," ","Affärsenhet:"," "]
[null,"Utvecklingsfilosofi:",null," ","Osäkerhetsdomän:"," "]
[]
[]
[null,"Bakgrund / Idé:\nBeskriv nuläge med problemet som ska lösas, eller möjligheten/marknadens behov.\n "]
[]
[null,"Projektets spelplan",null,"Planerat","Utfall",null,"Notering"]
[null,"Effektmål:"]
[]
[]
[]
[null,"Sammanfattande Projektmål:"]
[null,"Projektmål:"]
[]
[]
[]
[]
[null,"Avgränsningar:"]
[]
[]
[]
[null,"Förutsättningar:"]
[]
[null,"Ramar"]
[null,"   Startdatum:",null,"2024-01-11"]
[null,"   Slutdatum:",null,"2024-12-15"]
[null,"   Max antal persontimmar:"]
[null,"   Max kostnad:"]
[null,"   Reserv/riskbudget:"]
[null,"   Totalkostnad:",null,{"$f":"D33+D34","v":0},{"$f":"E33+E34","v":0},null,{"$f":"G33+G34","v":0}]
[]
[]
[null,"Kunder/Användare:\nBeskriver vem/vilka som använder projektets leverans.\n ",null,null,"Mottagare:\nBeskriver vem/vilka som ska förvalta resultatet efter leverans."]
[null,"Leveransbeskrivning:\nBeskriver hur resultatet ska levereras till kund/användare.",null,null,"Överlämningsbeskrivning:\nBeskriver hur överlämningen till mottagaren/mottagarna ska gå till."]
[null,"Väsentligaste Riskerna:\nBeskriver de allvarligaste riskerna som kan förhindra att projektet når sina mål eller som gör arbetet besvärligt."]
[]
[null,"Flexibilitetsmatris:\nÅsådliggör projektets flexibilitet avseende Tid, Kostnad och Resultat (en sak i respektive ruta)."]
[]
[null,"Mest flexibelt"]
[null,"Något flexibelt"]
[null,"Minst flexibelt"]

{"sheet":"Rev.historik","index":4,"n_rows":4,"n_cols":5,"rows_kept":4,"cut":false,"hidden":true,"merged":[[1,1,1,4]]}
[]
[]
[]
[null,"Version","Datum","Uppdaterad av","Kommentar"]

{"sheet":"Lärdomar","index":5,"n_rows":36,"n_cols":8,"rows_kept":36,"cut":false,"hidden":false,"merged":[[1,1,1,7],[3,1,3,7],[11,1,11,7],[29,1,29,7]]}
[]
[]
[]
[null,"Lärdomar från tidigare liknande initiativ"]
[null,"#","Nyckellärdomar från tidigare initiativ/projekt","Tidigare initiativ","Kontaktperson","Vad skall vi göra liknande?","Vad skall vi undvika att göra?","Övrig information"]
[null,1]
[null,2]
[null,3]
[null,4]
[null,5]
[]
[null,"Lärdomar under projektet"]
[null,"#","Lärdom under projektet","Datum loggat","Fortsätta göra","Börja göra","Sluta göra","Övrig information"]
[null,1]
[null,2]
[null,3]
[null,4]
[null,5]
[null,6]
[null,7]
[null,8]
[null,9]
[null,10]
[null,11]
[null,12]
[null,13]
[null,14]
[null,15]
[]
[null,"Summering av viktigaste lärdomarna från detta projekt samt hur sprida"]
[null,"#","Nyckellärdom från detta projekt","Typ av lärdom","Vem/vilka kan ha nytta av detta","Hur sprida till andra berörda","Vem är ansvarig att sprida lärdomen","När skall det vara gjort"]
[null,1]
[null,2]
[null,3]
[null,4]
[null,5]

{"sheet":"Intressenter","index":6,"n_rows":5,"n_cols":8,"rows_kept":5,"cut":false,"hidden":false,"merged":[[3,7,4,7],[1,1,1,6],[3,1,3,2],[3,3,4,3],[3,4,4,4],[3,5,4,5],[3,6,4,6]]}
[]
[]
[]
[null,"Intressent",null,"Resultat- eller Genomförande-intressent","Primär, Sekundär, eller Tertiär","Inställning till projektet","Beskriv behov eller förväntningar för respektive intressent. (Var specifik).","Hantering"]
[null,"Namn","Roll"]

{"sheet":"Funk.str","index":7,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"Lev.str","index":8,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"Arb.str","index":9,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"Produktbacklog","index":10,"n_rows":4,"n_cols":8,"rows_kept":4,"cut":false,"hidden":false,"merged":[[1,1,1,7]]}
[]
[]
[]
[null,"Id #","Kategori","Beskrivning","Prioritet","Estimat","Acceptanskriterier","Status"]

{"sheet":"Visualisering","index":11,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[[1,1,1,7]]}

{"sheet":"Organisation","index":12,"n_rows":23,"n_cols":7,"rows_kept":23,"cut":false,"hidden":false,"merged":[[1,1,1,7]]}
[]
[]
[]
[]
[]
[null,null,"Resursansvariga:",null,"Ansvarig ledning:",null,"Kund / Användare:"]
[]
[]
[]
[]
[null,null,null,null,"Styrgrupp:"]
[null,null,null,null,null,null,"Mottagare:"]
[]
[]
[]
[]
[]
[null,null,null,null,"Projektbeställare:"]
[null,null,null,null,null,null,"Projektledare:"]
[null,null,"Referensnätverk (Intressenter, specialister etc):"]
[]
[]
[null,null,null,null,null,null,"Projektgrupp (inkl. ev. delprojekt, etc):"]

{"sheet":"Resursplan","index":13,"n_rows":47,"n_cols":55,"rows_kept":47,"cut":false,"hidden":false,"merged":[[1,1,1,24],[18,1,20,1],[18,2,20,2],[21,1,23,1],[21,2,23,2],[5,4,7,4],[9,1,11,1],[9,2,11,2],[5,6,7,6],[5,2,7,2],[5,1,7,1],[5,5,7,5],[4,5,4,6],[3,5,3,6],[24,2,26,2],[24,1,26,1],[12,1,14,1],[12,2,14,2],[15,1,17,1],[15,2,17,2],[40,1,42,1],[34,2,36,2],[40,2,42,2],[27,1,29,1],[27,2,29,2],[30,2,32,2],[30,1,32,1],[37,1,39,1],[37,2,39,2],[34,1,36,1]]}
[]
[]
[]
[null,null,null,null,"Startdatum:","Slutdatum:"]
[null,null,null,null,{"$f":"Proj.beställning!D30","v":"2024-01-11"},{"$f":"Proj.beställning!D31","v":"2024-12-15"}]
[null,"Namn/roll","Resursansvarig               (Linjechef) ",null,"Datum för uppdatering","Status\n(resurser säkrade?)","Timmar totalt","2024","","","","","","","","","",""]
[null,null,null,null,null,null,null,"jan","","","","feb","","","","mar","","",null,"apr",null,null,null,null,"maj",null,null,null,"jun",null,null,null,"jul",null,null,null,null,"aug",null,null,null,"sep",null,null,null,null,"okt",null,null,null,"nov",null,null,null,"dec"]
[null,null,null,null,null,null,null,"w: 2","w: 3","w: 4","w: 5","w: 6","w: 7","w: 8","w: 9","w: 10","w: 11","w: 12","w: 13","w: 14","w: 15","w: 16","w: 17","w: 18","w: 19","w: 20","w: 21","w: 22","w: 23","w: 24","w: 25","w: 26","w: 27","w: 28","w: 29","w: 30","w: 31","w: 32","w: 33","w: 34","w: 35","w: 36","w: 37","w: 38","w: 39","w: 40","w: 41","w: 42","w: 43","w: 44","w: 45","w: 46","w: 47","w: 48","w: 49"]
[null,"Anställda"]
[null,null,null,"Resursram:",null,null,{"$f":"SUM(H10:AN10)","v":0}]
[null,null,null,"Faktiskt utfall:",null,null,0]
[null,null,null,"Estimerat:",null,null,0]
[null,null,null,"Resursram:",null,null,0]
[null,null,null,"Faktiskt utfall:",null,null,0]
[null,null,null,"Estimerat:",null,null,0]
[null,null,null,"Resursram:",null,null,{"$f":"SUM(H16:AN16)","v":0}]
[null,null,null,"Faktiskt utfall:",null,null,0]
[null,null,null,"Estimerat:",null,null,0]
[null,null,null,"Resursram:",null,null,{"$f":"SUM(H19:AN19)","v":0}]
[null,null,null,"Faktiskt utfall:",null,null,0]
[null,null,null,"Estimerat:",null,null,0]
[null,null,null,"Resursram:",null,null,{"$f":"SUM(H22:AN22)","v":0}]
[null,null,null,"Faktiskt utfall:",null,null,0]
[null,null,null,"Estimerat:",null,null,0]
[null,null,null,"Resursram:",null,null,0]
[null,null,null,"Faktiskt utfall:",null,null,0]
[null,null,null,"Estimerat:",null,null,0]
[null,null,null,"Resursram:",null,null,{"$f":"SUM(H28:AN28)","v":0}]
[null,null,null,"Faktiskt utfall:",null,null,0]
[null,null,null,"Estimerat:",null,null,0]
[null,null,null,"Resursram:",null,null,0]
[null,null,null,"Faktiskt utfall:",null,null,0]
[null,null,null,"Estimerat:",null,null,0]
[null,"Konsulter"]
[null,null,null,"Resursram:",null,null,{"$f":"SUM(H35:AN35)","v":0}]
[null,null,null,"Faktiskt utfall:",null,null,0]
[null,null,null,"Estimerat:",null,null,0]
[null,null,null,"Resursram:",null,null,{"$f":"SUM(H38:AN38)","v":0}]
[null,null,null,"Faktiskt utfall:",null,null,0]
[null,null,null,"Estimerat:",null,null,0]
[null,null,null,"Resursram:",null,null,0]
[null,null,null,"Faktiskt utfall:",null,null,0]
[null,null,null,"Estimerat:",null,null,0]
[null,"Totalt"]
[null,null,null,"Resursram:",null,null,{"$f":"SUMIF($D$9:$D$44,$D45,G$9:G$44)","v":0},0,0,0,0,0,0,0,0,0,{"$f":"SUMIF($D$9:$D$44,$D45,Q$9:Q$44)","v":0},0,0,0,0,0,0,0,0,0,{"$f":"SUMIF($D$9:$D$44,$D45,AA$9:AA$44)","v":0},0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,null,null,"Faktiskt utfall:",null,null,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0]
[null,null,null,"Estimerat:",null,null,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0,0]

{"sheet":"Kom.plan","index":14,"n_rows":28,"n_cols":8,"rows_kept":28,"cut":false,"hidden":false,"merged":[[1,1,1,7],[16,1,16,7],[3,1,3,7]]}
[]
[]
[]
[null," Strategisk kommunikation"]
[null,"#","Intressent","Syfte","Metod","När/hur ofta","Ansvarig","Övrig information"]
[null,1]
[null,2]
[null,3]
[null,4]
[null,5]
[null,6]
[null,7]
[null,8]
[null,9]
[null,10]
[]
[null," Operativ kommunikation"]
[null,"#","Roll/grupp","Syfte","Metod","När/hur ofta","Ansvarig","Övrig information"]
[null,1]
[null,2]
[null,3]
[null,4]
[null,5]
[null,6]
[null,7]
[null,8]
[null,9]
[null,10]

{"sheet":"Gantt&MS","index":15,"n_rows":11,"n_cols":118,"rows_kept":11,"cut":false,"hidden":false,"merged":[[10,10,10,12],[11,10,11,12],[12,10,12,12],[13,10,13,12],[14,10,14,12],[5,10,5,12],[6,10,6,12],[9,10,9,12],[0,10,0,12],[1,10,1,12],[2,10,2,12],[3,10,3,12],[4,10,4,12],[5,1,5,2],[3,1,3,2],[4,1,4,2],[5,3,5,4],[4,3,4,4],[3,3,3,4],[30,10,30,12],[31,10,31,12],[32,10,32,12],[33,10,33,12],[34,10,34,12],[25,10,25,12],[26,10,26,12],[27,10,27,12],[28,10,28,12],[29,10,29,12],[20,10,20,12],[21,10,21,12],[22,10,22,12],[23,10,23,12],[24,10,24,12],[15,10,15,12],[16,10,16,12],[17,10,17,12],[18,10,18,12],[19,10,19,12],[50,10,50,12],[51,10,51,12],[52,10,52,12],[53,10,53,12],[54,10,54,12],[45,10,45,12],[46,10,46,12],[47,10,47,12],[48,10,48,12],[49,10,49,12],[40,10,40,12],[41,10,41,12],[42,10,42,12],[43,10,43,12],[44,10,44,12],[35,10,35,12],[36,10,36,12],[37,10,37,12],[38,10,38,12],[39,10,39,12],[70,10,70,12],[71,10,71,12],[72,10,72,12],[73,10,73,12],[74,10,74,12],[65,10,65,12],[66,10,66,12],[67,10,67,12],[68,10,68,12],[69,10,69,12],[60,10,60,12],[61,10,61,12],[62,10,62,12],[63,10,63,12],[64,10,64,12],[55,10,55,12],[56,10,56,12],[57,10,57,12],[58,10,58,12],[59,10,59,12],[90,10,90,12],[91,10,91,12],[92,10,92,12],[93,10,93,12],[94,10,94,12],[85,10,85,12],[86,10,86,12],[87,10,87,12],[88,10,88,12],[89,10,89,12],[80,10,80,12],[81,10,81,12],[82,10,82,12],[83,10,83,12],[84,10,84,12],[75,10,75,12],[76,10,76,12],[77,10,77,12],[78,10,78,12],[79,10,79,12],[110,10,110,12],[111,10,111,12],[112,10,112,12],[113,10,113,12],[114,10,114,12],[105,10,105,12],[106,10,106,12],[107,10,107,12],[108,10,108,12],[109,10,109,12],[100,10,100,12],[101,10,101,12],[102,10,102,12],[103,10,103,12],[104,10,104,12],[95,10,95,12],[96,10,96,12],[97,10,97,12],[98,10,98,12],[99,10,99,12],[130,10,130,12],[131,10,131,12],[132,10,132,12],[133,10,133,12],[134,10,134,12],[125,10,125,12],[126,10,126,12],[127,10,127,12],[128,10,128,12],[129,10,129,12],[120,10,120,12],[121,10,121,12],[122,10,122,12],[123,10,123,12],[124,10,124,12],[115,10,115,12],[116,10,116,12],[117,10,117,12],[118,10,118,12],[119,10,119,12],[150,10,150,12],[151,10,151,12],[152,10,152,12],[153,10,153,12],[154,10,154,12],[145,10,145,12],[146,10,146,12],[147,10,147,12],[148,10,148,12],[149,10,149,12],[140,10,140,12],[141,10,141,12],[142,10,142,12],[143,10,143,12],[144,10,144,12],[135,10,135,12],[136,10,136,12],[137,10,137,12],[138,10,138,12],[139,10,139,12],[170,10,170,12],[171,10,171,12],[172,10,172,12],[173,10,173,12],[174,10,174,12],[165,10,165,12],[166,10,166,12],[167,10,167,12],[168,10,168,12],[169,10,169,12],[160,10,160,12],[161,10,161,12],[162,10,162,12],[163,10,163,12],[164,10,164,12],[155,10,155,12],[156,10,156,12],[157,10,157,12],[158,10,158,12],[159,10,159,12],[190,10,190,12],[191,10,191,12],[192,10,192,12],[193,10,193,12],[194,10,194,12],[185,10,185,12],[186,10,186,12],[187,10,187,12],[188,10,188,12],[189,10,189,12],[180,10,180,12],[181,10,181,12],[182,10,182,12],[183,10,183,12],[184,10,184,12],[175,10,175,12],[176,10,176,12],[177,10,177,12],[178,10,178,12],[179,10,179,12],[210,10,210,12],[211,10,211,12],[212,10,212,12],[213,10,213,12],[214,10,214,12],[205,10,205,12],[206,10,206,12],[207,10,207,12],[208,10,208,12],[209,10,209,12],[200,10,200,12],[201,10,201,12],[202,10,202,12],[203,10,203,12],[204,10,204,12],[195,10,195,12],[196,10,196,12],[197,10,197,12],[198,10,198,12],[199,10,199,12],[230,10,230,12],[231,10,231,12],[232,10,232,12],[233,10,233,12],[234,10,234,12],[225,10,225,12],[226,10,226,12],[227,10,227,12],[228,10,228,12],[229,10,229,12],[220,10,220,12],[221,10,221,12],[222,10,222,12],[223,10,223,12],[224,10,224,12],[215,10,215,12],[216,10,216,12],[217,10,217,12],[218,10,218,12],[219,10,219,12],[250,10,250,12],[251,10,251,12],[252,10,252,12],[253,10,253,12],[254,10,254,12],[245,10,245,12],[246,10,246,12],[247,10,247,12],[248,10,248,12],[249,10,249,12],[240,10,240,12],[241,10,241,12],[242,10,242,12],[243,10,243,12],[244,10,244,12],[235,10,235,12],[236,10,236,12],[237,10,237,12],[238,10,238,12],[239,10,239,12],[270,10,270,12],[271,10,271,12],[272,10,272,12],[273,10,273,12],[274,10,274,12],[265,10,265,12],[266,10,266,12],[267,10,267,12],[268,10,268,12],[269,10,269,12],[260,10,260,12],[261,10,261,12],[262,10,262,12],[263,10,263,12],[264,10,264,12],[255,10,255,12],[256,10,256,12],[257,10,257,12],[258,10,258,12],[259,10,259,12],[290,10,290,12],[291,10,291,12],[292,10,292,12],[293,10,293,12],[294,10,294,12],[285,10,285,12],[286,10,286,12],[287,10,287,12],[288,10,288,12],[289,10,289,12],[280,10,280,12],[281,10,281,12],[282,10,282,12],[283,10,283,12],[284,10,284,12],[275,10,275,12],[276,10,276,12],[277,10,277,12],[278,10,278,12],[279,10,279,12],[310,10,310,12],[311,10,311,12],[312,10,312,12],[313,10,313,12],[314,10,314,12],[305,10,305,12],[306,10,306,12],[307,10,307,12],[308,10,308,12],[309,10,309,12],[300,10,300,12],[301,10,301,12],[302,10,302,12],[303,10,303,12],[304,10,304,12],[295,10,295,12],[296,10,296,12],[297,10,297,12],[298,10,298,12],[299,10,299,12],[330,10,330,12],[331,10,331,12],[332,10,332,12],[333,10,333,12],[334,10,334,12],[325,10,325,12],[326,10,326,12],[327,10,327,12],[328,10,328,12],[329,10,329,12],[320,10,320,12],[321,10,321,12],[322,10,322,12],[323,10,323,12],[324,10,324,12],[315,10,315,12],[316,10,316,12],[317,10,317,12],[318,10,318,12],[319,10,319,12],[350,10,350,12],[351,10,351,12],[352,10,352,12],[353,10,353,12],[354,10,354,12],[345,10,345,12],[346,10,346,12],[347,10,347,12],[348,10,348,12],[349,10,349,12],[340,10,340,12],[341,10,341,12],[342,10,342,12],[343,10,343,12],[344,10,344,12],[335,10,335,12],[336,10,336,12],[337,10,337,12],[338,10,338,12],[339,10,339,12],[370,10,370,12],[371,10,371,12],[372,10,372,12],[373,10,373,12],[374,10,374,12],[365,10,365,12],[366,10,366,12],[367,10,367,12],[368,10,368,12],[369,10,369,12],[360,10,360,12],[361,10,361,12],[362,10,362,12],[363,10,363,12],[364,10,364,12],[355,10,355,12],[356,10,356,12],[357,10,357,12],[358,10,358,12],[359,10,359,12],[390,10,390,12],[391,10,391,12],[392,10,392,12],[393,10,393,12],[394,10,394,12],[385,10,385,12],[386,10,386,12],[387,10,387,12],[388,10,388,12],[389,10,389,12],[380,10,380,12],[381,10,381,12],[382,10,382,12],[383,10,383,12],[384,10,384,12],[375,10,375,12],[376,10,376,12],[377,10,377,12],[378,10,378,12],[379,10,379,12],[410,10,410,12],[411,10,411,12],[412,10,412,12],[413,10,413,12],[414,10,414,12],[405,10,405,12],[406,10,406,12],[407,10,407,12],[408,10,408,12],[409,10,409,12],[400,10,400,12],[401,10,401,12],[402,10,402,12],[403,10,403,12],[404,10,404,12],[395,10,395,12],[396,10,396,12],[397,10,397,12],[398,10,398,12],[399,10,399,12],[430,10,430,12],[431,10,431,12],[432,10,432,12],[433,10,433,12],[434,10,434,12],[425,10,425,12],[426,10,426,12],[427,10,427,12],[428,10,428,12],[429,10,429,12],[420,10,420,12],[421,10,421,12],[422,10,422,12],[423,10,423,12],[424,10,424,12],[415,10,415,12],[416,10,416,12],[417,10,417,12],[418,10,418,12],[419,10,419,12],[450,10,450,12],[451,10,451,12],[452,10,452,12],[453,10,453,12],[454,10,454,12],[445,10,445,12],[446,10,446,12],[447,10,447,12],[448,10,448,12],[449,10,449,12],[440,10,440,12],[441,10,441,12],[442,10,442,12],[443,10,443,12],[444,10,444,12],[435,10,435,12],[436,10,436,12],[437,10,437,12],[438,10,438,12],[439,10,439,12],[470,10,470,12],[471,10,471,12],[472,10,472,12],[473,10,473,12],[474,10,474,12],[465,10,465,12],[466,10,466,12],[467,10,467,12],[468,10,468,12],[469,10,469,12],[460,10,460,12],[461,10,461,12],[462,10,462,12],[463,10,463,12],[464,10,464,12],[455,10,455,12],[456,10,456,12],[457,10,457,12],[458,10,458,12],[459,10,459,12],[490,10,490,12],[491,10,491,12],[492,10,492,12],[493,10,493,12],[494,10,494,12],[485,10,485,12],[486,10,486,12],[487,10,487,12],[488,10,488,12],[489,10,489,12],[480,10,480,12],[481,10,481,12],[482,10,482,12],[483,10,483,12],[484,10,484,12],[475,10,475,12],[476,10,476,12],[477,10,477,12],[478,10,478,12],[479,10,479,12],[510,10,510,12],[511,10,511,12],[512,10,512,12],[513,10,513,12],[514,10,514,12],[505,10,505,12],[506,10,506,12],[507,10,507,12],[508,10,508,12],[509,10,509,12],[500,10,500,12],[501,10,501,12],[502,10,502,12],[503,10,503,12],[504,10,504,12],[495,10,495,12],[496,10,496,12],[497,10,497,12],[498,10,498,12],[499,10,499,12],[530,10,530,12],[531,10,531,12],[532,10,532,12],[533,10,533,12],[534,10,534,12],[525,10,525,12],[526,10,526,12],[527,10,527,12],[528,10,528,12],[529,10,529,12],[520,10,520,12],[521,10,521,12],[522,10,522,12],[523,10,523,12],[524,10,524,12],[515,10,515,12],[516,10,516,12],[517,10,517,12],[518,10,518,12],[519,10,519,12],[550,10,550,12],[551,10,551,12],[552,10,552,12],[553,10,553,12],[554,10,554,12],[545,10,545,12],[546,10,546,12],[547,10,547,12],[548,10,548,12],[549,10,549,12],[540,10,540,12],[541,10,541,12],[542,10,542,12],[543,10,543,12],[544,10,544,12],[535,10,535,12],[536,10,536,12],[537,10,537,12],[538,10,538,12],[539,10,539,12],[570,10,570,12],[571,10,571,12],[572,10,572,12],[573,10,573,12],[574,10,574,12],[565,10,565,12],[566,10,566,12],[567,10,567,12],[568,10,568,12],[569,10,569,12],[560,10,560,12],[561,10,561,12],[562,10,562,12],[563,10,563,12],[564,10,564,12],[555,10,555,12],[556,10,556,12],[557,10,557,12],[558,10,558,12],[559,10,559,12],[590,10,590,12],[591,10,591,12],[592,10,592,12],[593,10,593,12],[594,10,594,12],[585,10,585,12],[586,10,586,12],[587,10,587,12],[588,10,588,12],[589,10,589,12],[580,10,580,12],[581,10,581,12],[582,10,582,12],[583,10,583,12],[584,10,584,12],[575,10,575,12],[576,10,576,12],[577,10,577,12],[578,10,578,12],[579,10,579,12],[610,10,610,12],[611,10,611,12],[612,10,612,12],[613,10,613,12],[614,10,614,12],[605,10,605,12],[606,10,606,12],[607,10,607,12],[608,10,608,12],[609,10,609,12],[600,10,600,12],[601,10,601,12],[602,10,602,12],[603,10,603,12],[604,10,604,12],[595,10,595,12],[596,10,596,12],[597,10,597,12],[598,10,598,12],[599,10,599,12],[630,10,630,12],[631,10,631,12],[632,10,632,12],[633,10,633,12],[634,10,634,12],[625,10,625,12],[626,10,626,12],[627,10,627,12],[628,10,628,12],[629,10,629,12],[620,10,620,12],[621,10,621,12],[622,10,622,12],[623,10,623,12],[624,10,624,12],[615,10,615,12],[616,10,616,12],[617,10,617,12],[618,10,618,12],[619,10,619,12],[650,10,650,12],[651,10,651,12],[652,10,652,12],[653,10,653,12],[654,10,654,12],[645,10,645,12],[646,10,646,12],[647,10,647,12],[648,10,648,12],[649,10,649,12],[640,10,640,12],[641,10,641,12],[642,10,642,12],[643,10,643,12],[644,10,644,12],[635,10,635,12],[636,10,636,12],[637,10,637,12],[638,10,638,12],[639,10,639,12],[670,10,670,12],[671,10,671,12],[672,10,672,12],[673,10,673,12],[674,10,674,12],[665,10,665,12],[666,10,666,12],[667,10,667,12],[668,10,668,12],[669,10,669,12],[660,10,660,12],[661,10,661,12],[662,10,662,12],[663,10,663,12],[664,10,664,12],[655,10,655,12],[656,10,656,12],[657,10,657,12],[658,10,658,12],[659,10,659,12],[690,10,690,12],[691,10,691,12],[692,10,692,12],[693,10,693,12],[694,10,694,12],[685,10,685,12],[686,10,686,12],[687,10,687,12],[688,10,688,12],[689,10,689,12],[680,10,680,12],[681,10,681,12],[682,10,682,12],[683,10,683,12],[684,10,684,12],[675,10,675,12],[676,10,676,12],[677,10,677,12],[678,10,678,12],[679,10,679,12],[710,10,710,12],[711,10,711,12],[712,10,712,12],[713,10,713,12],[714,10,714,12],[705,10,705,12],[706,10,706,12],[707,10,707,12],[708,10,708,12],[709,10,709,12],[700,10,700,12],[701,10,701,12],[702,10,702,12],[703,10,703,12],[704,10,704,12],[695,10,695,12],[696,10,696,12],[697,10,697,12],[698,10,698,12],[699,10,699,12],[730,10,730,12],[731,10,731,12],[732,10,732,12],[733,10,733,12],[734,10,734,12],[725,10,725,12],[726,10,726,12],[727,10,727,12],[728,10,728,12],[729,10,729,12],[720,10,720,12],[721,10,721,12],[722,10,722,12],[723,10,723,12],[724,10,724,12],[715,10,715,12],[716,10,716,12],[717,10,717,12],[718,10,718,12],[719,10,719,12],[750,10,750,12],[751,10,751,12],[752,10,752,12],[753,10,753,12],[754,10,754,12],[745,10,745,12],[746,10,746,12],[747,10,747,12],[748,10,748,12],[749,10,749,12],[740,10,740,12],[741,10,741,12],[742,10,742,12],[743,10,743,12],[744,10,744,12],[735,10,735,12],[736,10,736,12],[737,10,737,12],[738,10,738,12],[739,10,739,12],[770,10,770,12],[771,10,771,12],[772,10,772,12],[773,10,773,12],[774,10,774,12],[765,10,765,12],[766,10,766,12],[767,10,767,12],[768,10,768,12],[769,10,769,12],[760,10,760,12],[761,10,761,12],[762,10,762,12],[763,10,763,12],[764,10,764,12],[755,10,755,12],[756,10,756,12],[757,10,757,12],[758,10,758,12],[759,10,759,12],[790,10,790,12],[791,10,791,12],[792,10,792,12],[793,10,793,12],[794,10,794,12],[785,10,785,12],[786,10,786,12],[787,10,787,12],[788,10,788,12],[789,10,789,12],[780,10,780,12],[781,10,781,12],[782,10,782,12],[783,10,783,12],[784,10,784,12],[775,10,775,12],[776,10,776,12],[777,10,777,12],[778,10,778,12],[779,10,779,12],[810,10,810,12],[811,10,811,12],[812,10,812,12],[813,10,813,12],[814,10,814,12],[805,10,805,12],[806,10,806,12],[807,10,807,12],[808,10,808,12],[809,10,809,12],[800,10,800,12],[801,10,801,12],[802,10,802,12],[803,10,803,12],[804,10,804,12],[795,10,795,12],[796,10,796,12],[797,10,797,12],[798,10,798,12],[799,10,799,12],[830,10,830,12],[831,10,831,12],[832,10,832,12],[833,10,833,12],[834,10,834,12],[825,10,825,12],[826,10,826,12],[827,10,827,12],[828,10,828,12],[829,10,829,12],[820,10,820,12],[821,10,821,12],[822,10,822,12],[823,10,823,12],[824,10,824,12],[815,10,815,12],[816,10,816,12],[817,10,817,12],[818,10,818,12],[819,10,819,12],[850,10,850,12],[851,10,851,12],[852,10,852,12],[853,10,853,12],[854,10,854,12],[845,10,845,12],[846,10,846,12],[847,10,847,12],[848,10,848,12],[849,10,849,12],[840,10,840,12],[841,10,841,12],[842,10,842,12],[843,10,843,12],[844,10,844,12],[835,10,835,12],[836,10,836,12],[837,10,837,12],[838,10,838,12],[839,10,839,12],[870,10,870,12],[871,10,871,12],[872,10,872,12],[873,10,873,12],[874,10,874,12],[865,10,865,12],[866,10,866,12],[867,10,867,12],[868,10,868,12],[869,10,869,12],[860,10,860,12],[861,10,861,12],[862,10,862,12],[863,10,863,12],[864,10,864,12],[855,10,855,12],[856,10,856,12],[857,10,857,12],[858,10,858,12],[859,10,859,12],[890,10,890,12],[891,10,891,12],[892,10,892,12],[893,10,893,12],[894,10,894,12],[885,10,885,12],[886,10,886,12],[887,10,887,12],[888,10,888,12],[889,10,889,12],[880,10,880,12],[881,10,881,12],[882,10,882,12],[883,10,883,12],[884,10,884,12],[875,10,875,12],[876,10,876,12],[877,10,877,12],[878,10,878,12],[879,10,879,12],[910,10,910,12],[911,10,911,12],[912,10,912,12],[913,10,913,12],[914,10,914,12],[905,10,905,12],[906,10,906,12],[907,10,907,12],[908,10,908,12],[909,10,909,12],[900,10,900,12],[901,10,901,12],[902,10,902,12],[903,10,903,12],[904,10,904,12],[895,10,895,12],[896,10,896,12],[897,10,897,12],[898,10,898,12],[899,10,899,12],[930,10,930,12],[931,10,931,12],[932,10,932,12],[933,10,933,12],[934,10,934,12],[925,10,925,12],[926,10,926,12],[927,10,927,12],[928,10,928,12],[929,10,929,12],[920,10,920,12],[921,10,921,12],[922,10,922,12],[923,10,923,12],[924,10,924,12],[915,10,915,12],[916,10,916,12],[917,10,917,12],[918,10,918,12],[919,10,919,12],[950,10,950,12],[951,10,951,12],[952,10,952,12],[953,10,953,12],[954,10,954,12],[945,10,945,12],[946,10,946,12],[947,10,947,12],[948,10,948,12],[949,10,949,12],[940,10,940,12],[941,10,941,12],[942,10,942,12],[943,10,943,12],[944,10,944,12],[935,10,935,12],[936,10,936,12],[937,10,937,12],[938,10,938,12],[939,10,939,12],[970,10,970,12],[971,10,971,12],[972,10,972,12],[973,10,973,12],[974,10,974,12],[965,10,965,12],[966,10,966,12],[967,10,967,12],[968,10,968,12],[969,10,969,12],[960,10,960,12],[961,10,961,12],[962,10,962,12],[963,10,963,12],[964,10,964,12],[955,10,955,12],[956,10,956,12],[957,10,957,12],[958,10,958,12],[959,10,959,12],[990,10,990,12],[991,10,991,12],[992,10,992,12],[993,10,993,12],[994,10,994,12],[985,10,985,12],[986,10,986,12],[987,10,987,12],[988,10,988,12],[989,10,989,12],[980,10,980,12],[981,10,981,12],[982,10,982,12],[983,10,983,12],[984,10,984,12],[975,10,975,12],[976,10,976,12],[977,10,977,12],[978,10,978,12],[979,10,979,12],[1010,10,1010,12]],"merged_total":1229,"flags":["merged_cut"]}
[]
[]
[]
[null,"Fas:"]
[null,"Start:",null,{"$f":"Proj.beställning!D30","v":"2024-01-11"}]
[null,"Slut",null,{"$f":"Proj.beställning!D31","v":"2024-12-15"}]
[]
[null,"För närzonsplanering som Kanban använd",null,"Typ",null,null,null,"Extrainformation",null,null,null,null,null,null,"2024"]
[null,"annat verktyg som Tasks i MS Teams",null,"(Aktivitet,","Varaktighet","Faktiskt eller",null,null,null,null,null,null,null,null,"jan",null,null,null,"feb",null,null,null,"mar",null,null,null,"apr",null,null,null,null,"maj",null,null,null,"jun",null,null,null,"jul",null,null,null,null,"aug",null,null,null,"sep",null,null,null,null,"okt",null,null,null,"nov",null,null,null,"dec",null,"okt",null,null,null,"nov",null,null,null,"dec",null,null,null,"mar",null,null,null,null,"apr",null,null,null,"maj",null,null,null,"jun",null,null,null,null,"jul",null,null,null,"aug",null,null,null,"sep",null,null,null,null,"okt",null,null,null,"nov",null,null,null,"dec"]
[null,null,null,"Grind (G),","Ledtid","estimerat startdatum","Slutdatum","Spara fastställda",null,null,null,null,null,null,2,3,4,5,6,7,8,9,10,11,12,13,14,15,16,17,18,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,37,38,39,40,41,42,43,44,45,46,47,48,49,40,41,42,43,44,45,46,47,48,49,7,8,9,10,11,12,13,14,15,16,17,18,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35,36,37,38,39,40,41,42,43,44,45,46,47,48,49,50,51,52]
[null,"Nr","Namn","Milstolpe)","(Kal.dagar)","(t.ex. 2014-02-28)","(beräknas)","milstolpe-datum","Arbete (timmar)","Acceptanskriterier för milstolpen","Status",null,null,"Ansvarig",8,15,22,29,5,12,19,26,4,11,18,25,1,8,15,22,29,6,13,20,27,3,10,17,24,1,8,15,22,29,5,12,19,26,2,9,16,23,30,7,14,21,28,4,11,18,25,2,30,7,14,21,28,4,11,18,25,2,10,17,24,3,10,17,24,31,7,14,21,28,5,12,19,26,2,9,16,23,30,7,14,21,28,4,11,18,25,1,8,15,22,29,6,13,20,27,3,10,17,24,1,8,15,22]

{"sheet":"Risker","index":16,"n_rows":41,"n_cols":12,"rows_kept":41,"cut":false,"hidden":false,"merged":[[1,1,1,11],[6,9,6,11],[3,1,3,2],[4,1,4,2]]}
[]
[]
[]
[null,"Senaste riskanalys genomfördes:",null,null,"Använd datumformat"]
[null,"Nästa riskanalys genomförs (plan):",null,null,"      2023-02-28"]
[]
[null,"Riskanalys före åtgärd",null,null,null,null,null,null,null,"Efter åtgärd"]
[null,"Risk #","Risk","Riskbeskrivning - inklusive förtydligande av risken och dess potentiella effekt","Dokumenterad Datum","Sanno-\nlikhet","Konse-\nkvens","Riskvärde"," Riskägare","Sanno-\nlikhet","Konse-\nkvens","Riskvärde"]
[null,"R.1",null,null,null,null,null,{"$f":"IF(F9=\"\",\"\",F9*G9)","v":""},null,null,null,{"$f":"IF(J9=\"\",\"\",J9*K9)","v":""}]
[null,"R.2",null,null,null,null,null,"",null,null,null,""]
[null,"R.3",null,null,null,null,null,"",null,null,null,""]
[null,"R.4",null,null,null,null,null,{"$f":"IF(F12=\"\",\"\",F12*G12)","v":""},null,null,null,{"$f":"IF(J12=\"\",\"\",J12*K12)","v":""}]
[null,"R.5",null,null,null,null,null,{"$f":"IF(F13=\"\",\"\",F13*G13)","v":""},null,null,null,""]
[null,"R.6",null,null,null,null,null,"",null,null,null,{"$f":"IF(J14=\"\",\"\",J14*K14)","v":""}]
[null,"R.7",null,null,null,null,null,"",null,null,null,""]
[null,"R.8",null,null,null,null,null,"",null,null,null,""]
[null,"R.9",null,null,null,null,null,"",null,null,null,""]
[null,"R.10",null,null,null,null,null,"",null,null,null,""]
[null,"R.11",null,null,null,null,null,"",null,null,null,""]
[null,"R.12",null,null,null,null,null,"",null,null,null,""]
[null,"R.13",null,null,null,null,null,"",null,null,null,""]
[null,"R.14",null,null,null,null,null,"",null,null,null,""]
[null,"R.15",null,null,null,null,null,"",null,null,null,""]
[null,"R.16",null,null,null,null,null,"",null,null,null,""]
[null,"R.17",null,null,null,null,null,"",null,null,null,""]
[null,"R.18",null,null,null,null,null,"",null,null,null,""]
[null,"R.19",null,null,null,null,null,"",null,null,null,""]
[null,"R.20",null,null,null,null,null,"",null,null,null,""]
[null,"R.21",null,null,null,null,null,"",null,null,null,""]
[null,"R.22",null,null,null,null,null,"",null,null,null,""]
[null,"R.23",null,null,null,null,null,"",null,null,null,""]
[null,"R.24",null,null,null,null,null,"",null,null,null,""]
[null,"R.25",null,null,null,null,null,"",null,null,null,""]
[null,"R.26",null,null,null,null,null,"",null,null,null,""]
[null,"R.27",null,null,null,null,null,"",null,null,null,""]
[null,"R.28",null,null,null,null,null,{"$f":"IF(F36=\"\",\"\",F36*G36)","v":""},null,null,null,{"$f":"IF(J36=\"\",\"\",J36*K36)","v":""}]
[null,"R.29",null,null,null,null,null,"",null,null,null,""]
[null,"R.30",null,null,null,null,null,"",null,null,null,""]
[null,"R.31",null,null,null,null,null,"",null,null,null,""]
[null,"R.32",null,null,null,null,null,"",null,null,null,""]
[null,"R.33",null,null,null,null,null,"",null,null,null,""]

{"sheet":"Risk Åtg.","index":17,"n_rows":37,"n_cols":9,"rows_kept":37,"cut":false,"hidden":false,"merged":[[1,1,1,8]]}
[]
[]
[]
[null,"Åtgärd #","Riskbeskrivning - från analysbladet\n(använd drop-down-menyn)","Föreslagen åtgärd\n(tänk på att minska både sannolikhet och konsekvens)","Kostnad för åtgården\n(Tid/Pengar/Resurser)","Göra?     Ja/Nej","Ansvarig för åtgärden","Klart datum","Status"]
[null,"A.1"]
[null,"A.2"]
[null,"A.3"]
[null,"A.4"]
[null,"A.5"]
[null,"A.6"]
[null,"A.7"]
[null,"A.8"]
[null,"A.9"]
[null,"A.10"]
[null,"A.11"]
[null,"A.12"]
[null,"A.13"]
[null,"A.14"]
[null,"A.15"]
[null,"A.16"]
[null,"A.17"]
[null,"A.18"]
[null,"A.19"]
[null,"A.20"]
[null,"A.21"]
[null,"A.22"]
[null,"A.23"]
[null,"A.24"]
[null,"A.25"]
[null,"A.26"]
[null,"A.27"]
[null,"A.28"]
[null,"A.29"]
[null,"A.30"]
[null,"A.31"]
[null,"A.32"]
[null,"A.33"]

{"sheet":"Möjligheter","index":18,"n_rows":41,"n_cols":12,"rows_kept":41,"cut":false,"hidden":false,"merged":[[1,1,1,11],[3,1,3,2],[4,1,4,2],[6,9,6,11]]}
[]
[]
[]
[null,"Senaste möjlighetsanalys genomfördes:",null,null,"Använd datumformat"]
[null,"Nästa möjlighetsanalys genomförs (plan):",null,null,"      2023-02-28"]
[]
[null,"Möjlighetsanalys före åtgärd",null,null,null,null,null,null,null,"Efter åtgärd"]
[null,"Möjl #","Möjlighet","Möjlighetsbeskrivning - \ninklusive förtydligande av möjligheten och dess potentiella effekt","Dokumenterad Datum","Sanno-\nlikhet","Konse-\nkvens","Möjlighets-värde"," Möjlighetsägare","Sanno-\nlikhet","Konse-\nkvens","Möjlighets-värde"]
[null,"M.1",null,null,null,null,null,{"$f":"IF(F9=\"\",\"\",F9*G9)","v":""},null,null,null,{"$f":"IF(J9=\"\",\"\",J9*K9)","v":""}]
[null,"M.2",null,null,null,null,null,"",null,null,null,""]
[null,"M.3",null,null,null,null,null,"",null,null,null,""]
[null,"M.4",null,null,null,null,null,{"$f":"IF(F12=\"\",\"\",F12*G12)","v":""},null,null,null,{"$f":"IF(J12=\"\",\"\",J12*K12)","v":""}]
[null,"M.5",null,null,null,null,null,{"$f":"IF(F13=\"\",\"\",F13*G13)","v":""},null,null,null,""]
[null,"M.6",null,null,null,null,null,"",null,null,null,{"$f":"IF(J14=\"\",\"\",J14*K14)","v":""}]
[null,"M.7",null,null,null,null,null,"",null,null,null,""]
[null,"M.8",null,null,null,null,null,"",null,null,null,""]
[null,"M.9",null,null,null,null,null,"",null,null,null,""]
[null,"M.10",null,null,null,null,null,"",null,null,null,""]
[null,"M.11",null,null,null,null,null,"",null,null,null,""]
[null,"M.12",null,null,null,null,null,"",null,null,null,""]
[null,"M.13",null,null,null,null,null,"",null,null,null,""]
[null,"M.14",null,null,null,null,null,"",null,null,null,""]
[null,"M.15",null,null,null,null,null,"",null,null,null,""]
[null,"M.16",null,null,null,null,null,"",null,null,null,""]
[null,"M.17",null,null,null,null,null,"",null,null,null,""]
[null,"M.18",null,null,null,null,null,"",null,null,null,""]
[null,"M.19",null,null,null,null,null,"",null,null,null,""]
[null,"M.20",null,null,null,null,null,"",null,null,null,""]
[null,"M.21",null,null,null,null,null,"",null,null,null,""]
[null,"M.22",null,null,null,null,null,"",null,null,null,""]
[null,"M.23",null,null,null,null,null,"",null,null,null,""]
[null,"M.24",null,null,null,null,null,"",null,null,null,""]
[null,"M.25",null,null,null,null,null,"",null,null,null,""]
[null,"M.26",null,null,null,null,null,"",null,null,null,""]
[null,"M.27",null,null,null,null,null,"",null,null,null,""]
[null,"M.28",null,null,null,null,null,"",null,null,null,""]
[null,"M.29",null,null,null,null,null,"",null,null,null,""]
[null,"M.30",null,null,null,null,null,"",null,null,null,""]
[null,"M.31",null,null,null,null,null,"",null,null,null,""]
[null,"M.32",null,null,null,null,null,"",null,null,null,""]
[null,"M.33",null,null,null,null,null,"",null,null,null,""]

{"sheet":"Möjl.Åtg","index":19,"n_rows":37,"n_cols":9,"rows_kept":37,"cut":false,"hidden":false,"merged":[[1,1,1,8]]}
[]
[]
[]
[null,"Åtgärd #","Möjlighetsbeskrivning - från analysbladet\n(använd drop-down-menyn)","Föreslagen åtgärd\n(tänk på att öka både sannolikhet och konsekvens)","Kostnad för åtgården\n(Tid/Pengar/Resurser)","Göra?     Ja/Nej","Ansvarig för åtgärden","Klart datum","Status"]
[null,"A.1"]
[null,"A.2"]
[null,"A.3"]
[null,"A.4"]
[null,"A.5"]
[null,"A.6"]
[null,"A.7"]
[null,"A.8"]
[null,"A.9"]
[null,"A.10"]
[null,"A.11"]
[null,"A.12"]
[null,"A.13"]
[null,"A.14"]
[null,"A.15"]
[null,"A.16"]
[null,"A.17"]
[null,"A.18"]
[null,"A.19"]
[null,"A.20"]
[null,"A.21"]
[null,"A.22"]
[null,"A.23"]
[null,"A.24"]
[null,"A.25"]
[null,"A.26"]
[null,"A.27"]
[null,"A.28"]
[null,"A.29"]
[null,"A.30"]
[null,"A.31"]
[null,"A.32"]
[null,"A.33"]

{"sheet":"Budget","index":20,"n_rows":14,"n_cols":8,"rows_kept":14,"cut":false,"hidden":false,"merged":[[1,1,1,7],[3,1,4,1],[3,2,3,3],[3,4,3,5],[3,6,3,7]]}
[]
[]
[]
[null,"Kostnadsslag","År 1",null,"År 2",null,"År 3"]
[null,null,"Budget","Utfall","Budget","Utfall","Budget","Utfall"]
[null,"Kostnad för mantimmar"]
[null,"Kostnad för konsulter"]
[null,"Material"]
[null,"Utrustning"]
[null,"Resor"]
[null,"Övrigt"]
[null,"Summa kostnad",{"$f":"SUM(C6:C11)","v":0},0,0,0,0,0]
[null,"Reserv"]
[null,"Totalkostnad",{"$f":"C12+C13","v":0},{"$f":"D12+D13","v":0},0,0,0,0]

{"sheet":"Status","index":21,"n_rows":23,"n_cols":10,"rows_kept":23,"cut":false,"hidden":false,"merged":[[16,7,16,9],[16,1,16,2],[13,1,13,2],[13,7,13,9],[20,3,20,9],[11,7,11,9],[1,1,1,9],[6,3,6,9],[18,3,18,9],[10,1,10,2],[12,1,12,2],[12,7,12,9],[14,1,14,2],[14,7,14,9],[9,7,9,9],[8,1,8,2],[8,7,8,9],[9,1,9,2],[10,7,10,9],[22,1,22,2],[8,3,8,4],[8,5,8,6],[22,3,22,9],[3,3,3,6],[15,7,15,9],[4,3,4,6],[20,1,20,2],[21,1,21,2],[18,1,18,2],[19,1,19,2],[15,1,15,2],[21,3,21,9],[19,3,19,9],[6,1,6,2],[11,1,11,2]]}
[]
[]
[]
[null,"Projektnamn",{"$f":"\"\" & Projektnamn","v":"Projektnamn"},"Projektledare",null,null,null,{"$f":"\"\" & Projektledare","v":" "},"Projektbeställare",{"$f":"\"\" & Projektbeställare","v":" "}]
[null,"Version",null,"Datum",null,null,null,null,"Projektfas"]
[]
[null,"Nyheter och resultat sedan förra rapporten i stort (kort)"]
[]
[null,"Parameter\n(värderas i förhållande till spelplan)",null,"Nuläge",null,"Prognos",null,"Kommentar"]
[null,"Effektmål",null,{"$f":"IFERROR(VLOOKUP(E10, RapportStatus, 2, FALSE), \"\")","v":""},null,{"$f":"IFERROR(VLOOKUP(G10, RapportStatus, 2, FALSE), \"\")","v":""}]
[null,"Projektmål",null,"",null,""]
[null,"Tid (kalendertid)",null,"",null,""]
[null,"Resurs (persontimmar)",null,"",null,""]
[null,"Resurs (kostnad)",null,{"$f":"IFERROR(VLOOKUP(E14, RapportStatus, 2, FALSE), \"\")","v":""},null,{"$f":"IFERROR(VLOOKUP(G14, RapportStatus, 2, FALSE), \"\")","v":""}]
[null,"Kvalitet",null,"",null,""]
[null,"Osäkerhet och risk",null,"",null,""]
[null,"Totalbedömning status och prognos",null,"",null,""]
[]
[null,"Behov av beslut och stöd"]
[null,"Omvärldsförändringar och dess påverkan på projektet"]
[null,"Lärdomar och hur dessa nyttjas"]
[null,"Viktiga milstolpar och aktiviteter för kommande period (kort)"]
[null,"Övrigt"]

{"sheet":"Beslutslogg","index":22,"n_rows":4,"n_cols":7,"rows_kept":4,"cut":false,"hidden":false,"merged":[[1,1,1,6]]}
[]
[]
[]
[null,"Beslut\n#","Ärende","Beslut ","Motiv för beslut","Datum för beslut","Beslutat av"]

{"sheet":"Ändringslogg","index":23,"n_rows":5,"n_cols":15,"rows_kept":5,"cut":false,"hidden":false,"merged":[[1,1,1,14],[3,6,3,10],[3,1,3,5]]}
[]
[]
[]
[null,"Ärende",null,null,null,null,"Status",null,null,null,null,"Beslut","Påverkan på","Risk","Ansvar"]
[null,"Nummer","Ändringsförslag\n(ref. till dok.)","Initierad av","Initierad\nDatum","Beslut\nkrävs senast Datum","Datum","Utredning","Redo för beslut","Godkänt","Avslaget","Beslutat av","Tidplan / Budget (kostnad) / Projektmål","Riskpåverkan","Ändringen bekostas av"]

{"sheet":"DA","index":24,"n_rows":11,"n_cols":3,"rows_kept":11,"cut":false,"hidden":true,"merged":[]}
["Chooseable sheets","Not Chooseable Sheets",false]
["Intressenter","Rev.Arena"]
["Budget","Menu"]
["Progress","DA"]
["Gantt&MS","Projektets Arena"]
["Organisation","Rev.Pop"]
["Kom.matris","Admin"]
["Risk1"]
["Beslutslogg"]
["Resursplan"]
["Ändringshantering"]

{"sheet":"Admin","index":25,"n_rows":49,"n_cols":6,"rows_kept":49,"cut":false,"hidden":true,"merged":[]}
[]
[]
[null,"Fokustriangel",null,null,null,"Status"]
[null,"Tid",null,null,null,"Planerad"]
[null,"Resurser / Kostnad",null,null,null,"Pågår"]
[null,"Projektmål / Resultat",null,null,null,"Klar"]
[]
[null,"Fokus",null,null,null,"Ja/Nej"]
[null,"Resultat",null,null,null,"Ja"]
[null,"Genomförande",null,null,null,"Nej"]
[]
[null,"Order",null,null,null,"Typ"]
[null,"Primär",null,null,null,"A"]
[null,"Sekundär",null,null,null,"G"]
[null,"Tertiär",null,null,null,"MS"]
[]
[null,"Attityd"]
[null,"Positiv"]
[null,"Neutral"]
[null,"Negativ"]
[]
[null,"Faser"]
[null,"Förstudie"]
[null,"Förberedelse"]
[null,"Genomförande"]
[null,"Avslut"]
[]
[null,"Utvecklingsfilosofi"]
[null,"Vattenfall"]
[null,"Integrationsdriven"]
[null,"Agil"]
[null,"Utforskande"]
[]
[null,"Osäkerhetsdomän"]
[null,"Enkel"]
[null,"Komplicerad"]
[null,"Komplex"]
[null,"Kaos"]
[]
[null,"Hantering"]
[null,"Involvera"]
[null,"Kommunicera"]
[null,"Informera"]
[null,"Bevaka"]
[]
[null,"RapportStatus"]
[null,"OK",1]
[null,"Varning",0]
[null,"Agera",-1]